## DFMEA Template
ATVC 2020 DFMEA Template | [6 empty] | Date:07/02/2020
mATV/eATV:mATV |  | Team ID:ATV93 | CAR NO.:93 |  |  |  | Team Name: CIET ENDEAVORS
Old/New Team:Old Team |  |  | Name of the College:Coimbatore Institute of Engineering Technology |  |  |  | Faculty Advisor: Seenivasan D
Team Member(s) Responsible: Siva hari T , Gobinath M , P.Mahesh ,
MODEL YEAR(s) / VEHICLE(s) : | [9 empty] | DFMEA date ( Orig. ) _( Rev.) _________
ITEM | Potential Failure Mode | Potential Effect(s) of Failures | sev | cla | Potential Cause(s)/Mechanism(s) of Failures | Occu | Current Design Control | Det | RPN | Recommended Action(s) | Responsibility & Target Completion Date | Action Results
Function |  |  |  | ss |  | re |  | ec |  |  |  | Action Taken | Sev | Occ | Det | RPN
Rollcage-Provides support and withstand the all forces caused due to sudden obstacles, braking or acceleration | Inappropriate welding as well as when the material is not chosen properly and design of the rollcage is not done properly | May lead to total collapse and severe damage to the vehicle | 8 |  | Improper design,material selection and design analysis | 9 | Accurate load calculation,proper research on available materials | 3 | 216 | SOLIDWORKS, ANSYS as per our requirments | Gobinath M (15-07-2019) | proper analysis and design implementation using softwares | 5 | 7 | 2 | 70
Steering System - It transmits steering effort to the wheel | Tie rod alignment and steering geometry | Chances of the accident is more due to unstablity of the vechile, failure of tyres contact with road | 7 |  | Improper ackerman geometry,steering effort design and mounting | 6 | calculations considering required steering geometry, | 4 | 168 | Proper allingments with accurate calculations | Narasingh kumar L (05-11-2019) | Ensure proper tie rod alignment and steering geometry along with acccurate calculations | 4 | 5 | 2 | 40
Drive Shaft - Power transmission from gearbox output shaft to rear wheels | failureof bearing and sleeve weld | Powertrain failure and arrest the vehicle drive | 9 |  | axis misalignment , wear and tear of bearing due to inadequate lubrication and improper clearance between rollcage and shaft | 5 | adequate lubrication,and mataining proper clearance | 7 | 315 | Changing the position of the respective member | Natrayasamy D (14-11-2019) | Making the necessary changes in the position of the shaft and align using V-block, bearings lubrication | 6 | 3 | 5 | 90
Brakes-Decelerate or decrease the speed of the vechile | Improper design of caliper mounting, incomplete bleeding | Low braking forces may lead to panic situation and also causes accidents | 8 |  | complex brake circuits, incomplete bleeding, and caliper mounting. | 7 | proper bleeding, selecting suitable brake caliper | 6 | 336 | Taking proper measures for bleeding and selecting caliper as per our requirements | Narasingh kumar L (20-11-2019) | Accurate design and braking calculations,taking proper measuers for brake bleeding | 5 | 4 | 6 | 120
Master Cylinder-Hydraulic actuator for braking | push rod failure, brake oil leakage | Insufficient fluid power transmission for braking | 6 |  | Improper selection of brake oil grade ,cylinder, restriction to the push rod movement | 6 | selecting proper brake oil with respect to cylider specification | 9 | 324 | push rod should have adequateD.O.F, removing dirt particles in it, | Deva Arul J (25-11-2019) | proper sealing of cylinder, using appropriate brake oil, proper maintanance of cylinder | 4 | 5 | 7 | 140

## DFMEA Guidelines
Guidelines:
Section A. | For eATV Teams: DFMEA has to be performed on Min. 2 out of the below 7 items/subsystems. Also, eATV teams need to perform DFMEA on mATV items/subsystems as mentioned below
| 1. Battery | Minimum 2 No's Items/subsystems are compulsory for eATV Teams | Minimum 5 No's of subsystems/items are compulsory
2. Battery Management System (BMS)
3. Motor
5. Controller
6. Transmission Coupling
7. Wiring Harness
Section B. | For mATV as well as eATV Teams, (Teams can choose Minimum "5/3" No's of items/subsystems as per their convenience)
1. Suspension System (Suspension Arms, Links, Ball Joints, Springs, Dampers, Suspension Mountings/Brackets)
2. Steering System (Steering Column, Tie Rod Ends, Rack and Pinion Assembly, Steering Wheel and Column UJ)
3. Brake System (Braking Performance, Caliper Mounts, Master Cylinder Mount, Brake Rotor)
4. Roll Cage
5.Transmission System (CVT Belt, Driveshaft, Gearbox, CVT Pulleys, Engine Mounting)
6. Upright
7. Tie Rod Ends
8. Wheel Hub
9. Wheel Bearings
10. Pedal Assembly
For, 1. eATV Teams: DFMEA needs to be performed on the Minimum "5" No's of items/subsystems ("2" No's from Section A & "3" No's from Section B)
2. mATV Teams: DFMEA needs to be performed on the Minimum "5" No's of items/subsystems ("5" No's from Section B)